## Phase 1
AI Analytics Portal — Phase 1: Revised Architecture ¦ 56 sub-tasks · 7 completed · 19 May – 6 Jun 2026
# | Module | Sub Module | Feature Detail | Task | Sub Task | Status | Hrs | Resource | Start | End | Notes
1 | Frontend | Analytics Portal | Layout & Shell | Build Analytics Portal shell | Create AnalyticsLayout.jsx with sidebar, top nav and route slots | Completed | 1 | Robin | 19-May-2026 | 19-May-2026
2 |  |  |  |  | Add Dashboard, Data Explorer and Chat route placeholders | Completed | 0.5 | Robin | 19-May-2026 | 19-May-2026
3 |  |  | Chat UI | Build Chat interface | Create ChatPage.jsx with message list, input bar and send button | Completed | 1.5 | Robin | 19-May-2026 | 19-May-2026
4 |  |  |  |  | Wire SSE stream to chat message list — render tokens as they arrive | Completed | 1 | Robin | 19-May-2026 | 19-May-2026 | SSE contract unchanged — backend swap is transparent
5 |  |  |  |  | Add loading spinner and error state for failed stream | Completed | 0.5 | Robin | 19-May-2026 | 19-May-2026
6 |  |  | Data Explorer | Build Data Explorer page | Create DataExplorer.jsx with table list panel and description sidebar | Completed | 1 | Robin | 19-May-2026 | 19-May-2026
7 |  |  |  |  | Add empty state and skeleton loader for table list | Completed | 0.5 | Robin | 19-May-2026 | 19-May-2026
8 | Infrastructure | Supabase Setup | pgvector | Enable pgvector extension | Run CREATE EXTENSION IF NOT EXISTS vector; in Supabase SQL editor | Not Started | 0.5 | Robin | 20-May-2026 | 20-May-2026 | One-time Supabase setup
9 |  |  |  |  | Confirm extension is active in Supabase dashboard extensions tab | Not Started | 0.5 | Robin | 20-May-2026 | 20-May-2026
10 |  |  | Vector Table | Create table_embeddings table | CREATE TABLE table_embeddings (table_name TEXT PRIMARY KEY, description TEXT, embedding VECTOR(384), column_hash TEXT, updated_at TIMESTAMPTZ) | Not Started | 1 | Robin | 20-May-2026 | 20-May-2026 | 384 dims = all-MiniLM-L6-v2
11 |  |  |  |  | CREATE INDEX ON table_embeddings USING hnsw (embedding vector_cosine_ops) for fast similarity search | Not Started | 0.5 | Robin | 20-May-2026 | 20-May-2026 | HNSW — fastest for cosine similarity at this scale
12 |  |  | FK Table | Create schema_relationships table | CREATE TABLE schema_relationships (from_table TEXT, to_table TEXT, from_col TEXT, to_col TEXT) | Not Started | 0.5 | Robin | 20-May-2026 | 20-May-2026 | Replaces in-memory dict as persistent FK source
13 |  |  |  |  | CREATE INDEX ON schema_relationships(from_table) for fast FK lookup at query time | Not Started | 0.5 | Robin | 20-May-2026 | 20-May-2026 | Shared across all cloud instances; survives restarts
14 |  |  | Cleanup | Remove ChromaDB | Remove chromadb from requirements.txt | Not Started | 0.25 | Robin | 20-May-2026 | 20-May-2026
15 |  |  |  |  | Delete vector_store/ directory from repo and update .gitignore | Not Started | 0.25 | Robin | 20-May-2026 | 20-May-2026
16 |  |  |  |  | Remove ChromaDB client init block from config.py | Not Started | 0.25 | Robin | 20-May-2026 | 20-May-2026
17 |  |  |  |  | Remove VECTOR_STORE_DIR path reference from all config and env files | Not Started | 0.25 | Robin | 20-May-2026 | 20-May-2026 | Saves ~400MB per deployment
18 | Core Engine | Schema Sync | Change Detection | MD5 hash check per table | On sync: compute MD5 of (column list + FK set) per table | Not Started | 1 | Robin | 21-May-2026 | 21-May-2026 | Prevents unnecessary Gemini API calls on every restart
19 |  |  |  |  | Compare hash against column_hash stored in table_embeddings | Not Started | 0.5 | Robin | 21-May-2026 | 21-May-2026
20 |  |  |  |  | Skip re-embedding if hash unchanged; only process new or modified tables | Not Started | 0.5 | Robin | 21-May-2026 | 21-May-2026
21 |  |  | LLM Description | Auto-describe tables via Gemini | For each new/changed table: send table_name + columns + 3 sample rows to Gemini (temperature=0) | Not Started | 1 | Robin | 21-May-2026 | 22-May-2026 | Temperature=0 for deterministic output
22 |  |  |  |  | Prompt: 'Write a 2-sentence business description of what this table stores.' Store result in table_embeddings.description | Not Started | 1 | Robin | 22-May-2026 | 22-May-2026
23 |  |  |  |  | Handle Gemini failures — fallback to column-list description if API call fails | Not Started | 0.5 | Robin | 22-May-2026 | 22-May-2026
24 |  |  | Embedding | Embed descriptions with all-MiniLM-L6-v2 | Run each Gemini-generated description through HuggingFace all-MiniLM-L6-v2 (local, CPU) | Not Started | 1 | Robin | 22-May-2026 | 22-May-2026 | Same model already in project — no new dependency
25 |  |  |  |  | Upsert 384-dim vector into table_embeddings.embedding via pgvector | Not Started | 0.5 | Robin | 22-May-2026 | 22-May-2026
26 |  |  | FK Persistence | Write FK rows to schema_relationships | For each table: use SQLAlchemy Inspector to get foreign_keys list | Not Started | 0.5 | Robin | 23-May-2026 | 23-May-2026
27 |  |  |  |  | DELETE existing rows for this table then INSERT fresh FK rows to remove stale entries | Not Started | 0.5 | Robin | 23-May-2026 | 23-May-2026
28 |  |  | Startup Hook | Wire sync_schema.py into FastAPI lifespan | Call sync_schema() inside FastAPI @asynccontextmanager lifespan on startup | Not Started | 0.5 | Robin | 23-May-2026 | 23-May-2026 | Fires automatically on every deploy
29 |  |  |  |  | Log output on startup: tables found, tables updated, tables skipped | Not Started | 0.5 | Robin | 23-May-2026 | 23-May-2026
30 |  | Query Pipeline | Semantic Retrieval | pgvector similarity search | Embed user question with all-MiniLM-L6-v2 on each query | Not Started | 1 | Robin | 26-May-2026 | 26-May-2026 | Direct replacement for ChromaDB similarity search
31 |  |  |  |  | Run: SELECT table_name FROM table_embeddings ORDER BY embedding <=> query_vec LIMIT 10 | Not Started | 1 | Robin | 26-May-2026 | 26-May-2026
32 |  |  |  |  | Return top-K=10 tables with similarity scores for downstream pruning | Not Started | 0.5 | Robin | 26-May-2026 | 27-May-2026
33 |  |  | FK Expansion | Load FK dict from Supabase on startup | At startup after sync: SELECT * FROM schema_relationships | Not Started | 0.5 | Robin | 27-May-2026 | 27-May-2026 | Persistent source solves multi-instance cloud problem
34 |  |  |  |  | Build Python dict {table: [neighbor_tables]} and cache on app state object | Not Started | 1 | Robin | 27-May-2026 | 27-May-2026 | In-memory for fast traversal; reloaded from Supabase on each restart
35 |  |  |  | 1-hop FK expansion | For each table in top-K, look up dict and add FK neighbours to expanded set | Not Started | 0.5 | Robin | 27-May-2026 | 27-May-2026
36 |  |  |  |  | Deduplicate expanded set and log final table count | Not Started | 0.5 | Robin | 27-May-2026 | 27-May-2026
37 |  |  |  |  | Pass full expanded set to SQL agent as context tables list | Not Started | 0.5 | Robin | 27-May-2026 | 27-May-2026
38 |  |  | Pruning | Layer 1 similarity threshold filter | After FK expansion: drop any added table whose cosine similarity is below 0.30 threshold | Not Started | 1 | Robin | 28-May-2026 | 28-May-2026
39 |  |  |  |  | Make threshold configurable via PRUNING_THRESHOLD in .env — default 0.30 | Not Started | 0.5 | Robin | 28-May-2026 | 28-May-2026
40 | Backend | REST Endpoints | Schema APIs | GET /api/schema/tables | New endpoint: query table_embeddings, return all tables with description and updated_at | Not Started | 1 | Robin | 28-May-2026 | 28-May-2026
41 |  |  |  |  | Add Pydantic response schema TableMetaOut with table_name, description, updated_at fields | Not Started | 0.5 | Robin | 28-May-2026 | 28-May-2026
42 |  |  |  | POST /api/schema/sync | New endpoint: manually trigger sync_schema() run | Not Started | 0.5 | Robin | 29-May-2026 | 29-May-2026
43 |  |  |  |  | Return SyncResult: tables_added, tables_updated, tables_skipped counts | Not Started | 0.5 | Robin | 29-May-2026 | 29-May-2026
44 |  |  | Chat API | Update POST /api/chat/stream | Swap ChromaDB retrieval call for pgvector similarity search function | Not Started | 1.5 | Robin | 29-May-2026 | 29-May-2026
45 |  |  |  |  | Swap in-memory dict lookup for FK dict loaded from app state (Supabase-backed) | Not Started | 1 | Robin | 29-May-2026 | 29-May-2026
46 |  |  |  |  | Confirm all SSE event types (tool_call, tool_result, response, done, error) still fire correctly | Not Started | 1 | Robin | 29-May-2026 | 29-May-2026
47 | QA | Schema Sync | Sync Test | QA — sync_schema.py | Add a test table to Supabase; restart backend | Not Started | 0.5 | Robin | 02-Jun-2026 | 02-Jun-2026
48 |  |  |  |  | Verify table appears in table_embeddings with correct description and embedding | Not Started | 0.5 | Robin | 02-Jun-2026 | 02-Jun-2026
49 |  |  |  |  | Verify FK rows written correctly to schema_relationships | Not Started | 0.5 | Robin | 02-Jun-2026 | 02-Jun-2026
50 |  |  |  |  | Verify unchanged tables are skipped on second restart (check startup logs) | Not Started | 0.5 | Robin | 02-Jun-2026 | 02-Jun-2026
51 |  | Query Pipeline | Retrieval Test | QA — pgvector similarity search | Run 8 representative natural language queries against the live system | Not Started | 1 | Robin | 03-Jun-2026 | 03-Jun-2026
52 |  |  |  |  | Verify correct tables in top-K; confirm FK neighbours included for join-heavy queries | Not Started | 1 | Robin | 03-Jun-2026 | 03-Jun-2026
53 |  |  | End-to-End | QA — full pipeline smoke test | Run 3 complex queries: natural language → pgvector → FK expansion → SQL → chart → SSE stream | Not Started | 1 | Robin | 04-Jun-2026 | 04-Jun-2026
54 |  |  |  |  | Verify SSE stream renders correctly in Chat UI — all event types fire as expected | Not Started | 1 | Robin | 04-Jun-2026 | 04-Jun-2026
55 |  |  | Bug Fixes | Bug fixes + README update | Fix any issues surfaced during QA sessions | Not Started | 2 | Robin | 05-Jun-2026 | 05-Jun-2026
56 |  |  |  |  | Update README: pgvector setup, schema_relationships, sync_schema.py, removed ChromaDB | Not Started | 1 | Robin | 05-Jun-2026 | 06-Jun-2026
|  |  |  | Phase 3 Total |  | Total Hours | 40.5